## Slide 1: Flower Power OHI Action Plan
High level plan
When does it start
Audience
Priority
Action
Result orientation
Operational Management
Vision/Mission/Values
Project Owners
Top 75
Selected group
Project Teams
All A2E trained employees
Top 75
BU Heads & Funct Leaders
Commercial
Selected employees
ExCo
All employees
Targeted Top75 & All employees
July 20th
Sept 9-11
Oct-Dec
Aug 15th
Oct
Aug 5th
July 2nd, 8th, 15th
July 21st
July 31st
Aug 1st
  Workshop Influence Model & Project Owner
  Workshop Ability to Execute – phase 1
  Train-the-trainer A2E
  Workshop Ability to Execute – phase 2
  Follow-up A2E with online teasers/training
  Guidelines Performance Review
  Check-in moments during weekly cadence
  Define plan of approach with Noelia
  VMV workshops
  VMV workshop with ExCo
  Define identity
  Communication approach
OHI Results
  Feedback global OHI results
  Share results with Leaders
  Train leaders to conduct workshops
  Leaders to conduct workshops
  Leaders to define action items with team
  Townhall sessions
  Consolidation of action items
All employees
Board & Top 75
BU Heads & Funct Leaders
BU Heads & Funct Leaders
BU Heads & Funct Leaders
All employees
ExCo
Early July
Early June
Early June
June/July
July 25th
July 1st and 2nd
Aug 1st
Progress
Ongoing
Awaiting VMV results and consolidation of team actions
Workshops ongoing
Awaiting translations
Completed
Completed
Ongoing
Completed