## Slide 1: Flower Power Timeline
Bottom-Up Planning
2
Developing a transformation plan (projects/financials) which is fully owned by line leaders
Transformation Implementation
3
Launching a full-scale effort to drive value to the bottom-line
How good could we be?
How do we get there?
Let’s make it happen!
Comprehensive understanding of the opportunity within DümmenOrange
The “Implementation Plan” – a fully integrated set of weekly deliverables
Rigorous delivery of performance, health and new capabilities
Quick wins: Capturing near term improvement opportunities
Independent Diligence
1
Establishing the trajectory and full potential of the business using an investor due diligence approach
March 24 - May 8
June 8 – Aug
Aug – Dec 2021

## Slide 2: FlowerPower’s approach
Bottom-Up Planning
Implementation
L2
L3
L4
L1
L5
L0
Track
Plan
Implement
Validate
Ideas
Realized
Requirements to pass the gate
An idea generated with a high level estimate of impact
Project owner identified
Estimate of value (with supporting documentation)
Idea analyzed for feasibility, impact and risks
L3, and L4 estimated dates
Detailed Bankable Plan (L4 date locked in)
KPIs to track delivery of impact
Where / how impact will be realized (impact tracking)
Health Actions to ensure successful Transformation
All Milestones in the Implementation plan required to ensure impact delivery are complete
Value accruing at run rate (recurring)
Full value accrued (one-time)
Health benefits sustained (Health)
In the course of the program, ideas are generated, defined in more detail specifying their impact, implementation requirements and
timeline. This is called a stage gate approach.